## Budget
Detailed 2-Month Timeline
1 | Weeks 1-3 (Pre-Production Phase):
This phase includes research, script development, and location scouting. The key tasks will focus on preparing the script, securing locations, and finalizing the crew. Here's the breakdown:
| Phase | Task | Activities | Particulars | No. of Units | Cost Per Unit (Ksh) | Total (Ksh)
| Research | Transport (Public/Uber) | Public transport for research | Lump sum | 1 | 3000 | 3000
|  | Internet | Internet for research and communication | Month | 1 | 3000 | 3000
|  | Participation Incentives | Incentives for people providing input | Per person | 5 | 600 | 3000
|  | Meals | Meals for research activities | Per day | 5 | 300 | 1500
| Writing | Script Development | Writer fees | Script finalization | 1 | 10000 | 10000
| Location Scouting | Transport (Public/Uber) | Public transport for location scouting | Lump sum | 1 | 2000 | 2000
|  | Location Fees | Fees for securing filming locations | Per location | 2 | 2000 | 4000
|  | Meals | Meals for scouting | Per day | 5 | 300 | 1500
28000
2 | Weeks 4-5 (Production Phase):
In this period, filming takes place. The production process will be tightly scheduled to fit into 10 days, using public transport/Ubers and meals for the crew. The necessary equipment will be rented, and key crew members will work within these two weeks.
| Phase | Task | Activities | Particulars | No. of Units / Frequency (months) | Cost Per Unit (Ksh) | Total (Ksh)
| Production | Equipment Rental & Purchase | Rental of essential equipment | 4K camera, Sound recorder | 1 | 25000 | 25000
|  |  | Purchasing of essential equipment | Gimbals | 1 | 15000 | 15000
|  |  |  | Lights | 2 | 15000 | 30000
|  |  |  | Reflectors | 5 | 400 | 2000
|  |  |  | SD Cards and other Equipment | 5 | 2500 | 12500
|  |  |  | Hardrives | 4 | 2500 | 10000
Crew
|  | Meals | Meals for crew during production | Lump sum | 2 | 5000 | 10000
|  | Transport (Public/Uber) | Uber or public transport for crew | Lump sum | 2 | 2500 | 5000
|  |  | Remuneration for crew members | Lump sum | 2 | 30000 | 60000
|  |  | Production Manager |  | 2 | 25000 | 50000
|  |  | Director |  | 2 | 25000 | 50000
|  |  | Director of Photography (DOP) |  | 2 | 15000 | 30000
|  |  | Producer |  | 2 | 20000 | 40000
|  |  | Location Manager |  | 2 | 15000 | 30000
109500
3 | Weeks 6-8 (Post-Production Phase):
Post-production will focus on editing, sound design, and the final assembly of the film. This will include tasks such as color grading, sound effects, and music synchronization. Marketing tasks will also start toward the end of this phase.
| Phase | Task | Activities | Particulars | No. of Units | Cost Per Unit (Ksh) | Total (Ksh)
| Post-Production | Editor Fees | Editing the video content | Editor's work | 1 | 22000 | 22000
|  | Sound Designer | Sound editing and music composition | Sound designer's work | 1 | 15000 | 15000
37000
4 | Week 8 and Beyond (Marketing and Distribution Phase):
Marketing efforts will involve submitting the film to festivals, creating promotional posters, and preparing for screenings. At this stage, the contingency fund will be available to cover any unexpected costs.
| Phase | Task | Activities | Particulars | No. of Units | Cost Per Unit (Ksh) | Total (Ksh)
| Marketing | Festival Submissions | Submissions to key film festivals | Lump sum | 1 | 7000 | 7000
|  | Posters | Creating and printing promotional posters | Lump sum | 1 | 6000 | 6000
13000
| Miscellaneous | Contingency | Reserve for unexpected costs | Contingency fund | Lump sum | 1 | 5000
Final Detailed Budget Summary
| Phase | Total Cost (Ksh)
| Pre-Production (Weeks 1-3) | 28000
| Production (Weeks 4-5) | 109500
| Post-Production (Weeks 6-8) | 37000
| Marketing & Miscellaneous | 13000
| Contingency Fund | 5000
| Grand Total | 192500
Key Notes:
Transport: Public transport and Uber costs have been accurately factored in as lump sums for each phase.
Crew: Payments for Director, DOP, and Sound Technician are based on realistic rates for short-term projects.
Contingency: A 5,000 Ksh contingency fund ensures flexibility for unforeseen expenses.
Timeline: The production is scheduled to be completed in two months, with filming compressed into a 10-day window and post-production taking three weeks.

## Activities
Activity Description | Costs | Stakeholders
Pre Production
Research | transport, Internet, particpation incentive, meals, subsitence expenses
writing | internet, writer fees
crewing | based on appointment
location scouting | Transport, meals, airtime, location fees<accomodation.
equipment sourcing | Test shoots Hiring, purchasing . | Hard drives, backups, gimbals, cameras, sound recorder, tripod, lights, reflector, drone, sd cards
Production
Shooting | Equipment Hiring, meals, transport, accomodation, airtime, Location Fees, Licences.
crew | Renumeration for crew members, Insurance. | Accountant, Prod. Man, DOP, Director, Producer, Location Manager.
Post Production
editing and colour grading | Editor Fees,
marketing & promotion | Festival fees, posters, banners,Marketer fees, ads sponsoring,
classification | Classification Fees.